## Timeline
Roadmap (Dec 2025 – Dec 2027)
Domain | Feature | Task | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027
Releases |  |  | R22 | R22 | R22 | R23 | R23 | R23 | R24 | R24 | R24 | R25 | R25 | R25 | R26 | R26 | R26 | R27 | R27 | R27 | R28 | R28 | R28 | R29 | R29 | R29 | R29
O&M Existing Tenant Apps | O&M Existing Tenant Apps | Existing Tenant O&M Support
Onboarding Tenant Apps | HSM DEV | HSM DEV (RMF 0-3)
HSM DEV Account Setup
HSM DEV Account Integration
HSM Multi-Tenant Resource Cleanup
| Tenant X PROD | Tenant X PROD (RMF 0-3)
Tenant X PROD Account Setup
Tenant X PROD Account Integration
Tenant X PROD ATO
| Onboarding Tenant Apps | NEW 1
NEW 3
Core Services | Kubernetes (Rancher) | Rancher RKE1 support
Rancher RKE2 development
Rancher RKE2 Tenant Migration
Rancher RKE2 Tenant Support
| Kubernetes (EKS) | EKS v1 support
AL2023 AMI hardening and STIG
EKS v2 config
Multi-cluster federation
| Kubernetes (EKS Auto) | EKS Auto Discovery
EKS Auto Platform Implementation
| Observability | Elastic Support
Prometheus/Grafana Support
Prometheus/Grafana Add-ons
Elastic Support
Prometheus/Grafana Support
| OAuth | Keycloak OAUTH2 Support
F5 Support
F5/DEX/OAUTH2 Developmment
F5/DEX/OAUTH2 Support
F5/DEX/OAUTH2 Support
| CICD | GitLab Support
Bitbucket -> GitLab Migration
| Image Repository | Harbor Implementation (CY failover)
Internal PROD ECR Implementation
Internal PROD ECR Migration
ECR Baseline
Resiliency | WEST Standalone Account | WEST Asset RMF (0-3)
WEST Standalone Asset Discovery
WEST Standalone Account Build
| EAST -> West Failover | EAST -> WEST Failover Discovery
EAST -> WEST Failover Implementation
EAST -> WEST Failover Testing
| FIS Implementation | FIS Support
Core Support Services | AI Enablements | Platform AI assistant beta
| Landing Page | Unified platform portal
FVEY C2S Core | FVEY C2S Core | Cross-domain service mesh
FVEY C2S Support | FVEY C2S Support | FVEY compliance automation
DEV C2S Core | DEV C2S Core | DEV enclave platform baseline
DEV C2S Support | DEV C2S Support | DEV enclave operational tooling
Legend:
Baseline (primary offering) | Green left accent | Optional | Orange dashed left accent

## Roadmap
domain | feature | task | start | end | notes | flag
O&M Existing Tenant Apps | O&M Existing Tenant Apps | Existing Tenant O&M Support | Dec 2025 | Dec 2027 | Reducing incident rate for Tier 1 tenants
Onboarding Tenant Apps | HSM DEV | HSM DEV (RMF 0-3) | Jan 2026 | Mar 2026
Onboarding Tenant Apps | HSM DEV | HSM DEV Account Setup | Mar 2026 | May 2026
Onboarding Tenant Apps | HSM DEV | HSM DEV Account Integration | May 2026 | Sep 2026
Onboarding Tenant Apps | HSM DEV | HSM Multi-Tenant Resource Cleanup | Aug 2026 | Sep 2026
Onboarding Tenant Apps | Tenant X PROD | Tenant X PROD (RMF 0-3) | Jan 2026 | Mar 2026
Onboarding Tenant Apps | Tenant X PROD | Tenant X PROD Account Setup | Mar 2026 | May 2026
Onboarding Tenant Apps | Tenant X PROD | Tenant X PROD Account Integration | May 2026 | Jul 2026
Onboarding Tenant Apps | Tenant X PROD | Tenant X PROD ATO | May 2026 | Jul 2026
Onboarding Tenant Apps | Onboarding Tenant Apps | NEW 1 | Jun 2026 | Aug 2026
Onboarding Tenant Apps | Onboarding Tenant Apps | NEW 3 | Jun 2026 | Aug 2026
Core Services | Kubernetes (Rancher) | Rancher RKE1 support | Dec 2025 | May 2026 | Initial EKS support through R2 | optional
Core Services | Kubernetes (Rancher) | Rancher RKE2 development | Dec 2025 | Mar 2026 | Initial EKS support through R2 | optional
Core Services | Kubernetes (Rancher) | Rancher RKE2 Tenant Migration | Apr 2026 | May 2026 | Initial EKS support through R2 | optional
Core Services | Kubernetes (Rancher) | Rancher RKE2 Tenant Support | Apr 2026 | Dec 2027 | Initial EKS support through R2 | optional
Core Services | Kubernetes (EKS) | EKS v1 support | Dec 2025 | May 2026 | Initial EKS support through R2 | baseline
Core Services | Kubernetes (EKS) | AL2023 AMI hardening and STIG | Jan 2026 | Mar 2026 | AMI hardening and STIG compliance | baseline
Core Services | Kubernetes (EKS) | EKS v2 config | Feb 2026 | Apr 2026 | EKS v2 configuration and rollout | baseline
Core Services | Kubernetes (EKS) | Multi-cluster federation | Feb 2026 | Jul 2026 | Enables regional failover | baseline
Core Services | Kubernetes (EKS Auto) | EKS Auto Discovery | Feb 2026 | Apr 2026 | Read up on EKS auto, meet w AWS for questions, deliver findings to client
Core Services | Kubernetes (EKS Auto) | EKS Auto Platform Implementation | Apr 2026 | Jun 2026 | Test EKS Auto, will have to have complete for Tenant X by 07-01
Core Services | Observability | Elastic Support | Dec 2025 | May 2026 | Standard observability stack | baseline
Core Services | Observability | Prometheus/Grafana Support | Dec 2025 | May 2026 | Standard observability stack | optional
Core Services | Observability | Prometheus/Grafana Add-ons | Dec 2025 | May 2026 | Standard observability stack | optional
Core Services | Observability | Elastic Support | May 2026 | Dec 2027 | Standard observability stack | optional
Core Services | Observability | Prometheus/Grafana Support | May 2026 | Dec 2027 | Standard observability stack | baseline
Core Services | OAuth | Keycloak OAUTH2 Support | Dec 2025 | May 2026 | External IdP federation | baseline
Core Services | OAuth | F5 Support | Dec 2025 | May 2026 | Removes dependency of IDAMS LDAP Password and resource configuration and O&M | optional
Core Services | OAuth | F5/DEX/OAUTH2 Developmment | Jan 2026 | May 2026 | Effectively replaces Keycloak so that we can move forward with less external dependencies and a lighter weight baseline to reduce O&M | baseline
Core Services | OAuth | F5/DEX/OAUTH2 Support | May 2026 | Dec 2027 | Effectively replaces Keycloak so that we can move forward with less external dependencies and a lighter weight baseline to reduce O&M | baseline
Core Services | OAuth | F5/DEX/OAUTH2 Support | May 2026 | Dec 2027 | Effectively replaces Keycloak so that we can move forward with less external dependencies and a lighter weight baseline to reduce O&M | baseline
Core Services | CICD | GitLab Support | Dec 2025 | Dec 2027 | Standardized pipelines across tenants, hardenening scripts, devops tools like certbot | baseline
Core Services | CICD | Bitbucket -> GitLab Migration | Sep 2026 | May 2027 | There might not be much of a reason to migrate from bitbucket other than consistency but it needs to be understood how we can keep the tf state the same if we execute migration
Core Services | Image Repository | Harbor Implementation (CY failover) | Dec 2025 | Mar 2026 | CY failover solution to maintain platform conainer images
Core Services | Image Repository | Internal PROD ECR Implementation | Jan 2026 | Mar 2026 | Test AMI pipeline images to ECR
Core Services | Image Repository | Internal PROD ECR Migration | Mar 2026 | May 2026 | Migrate all platform images to ECR
Core Services | Image Repository | ECR Baseline | May 2026 | Dec 2027 | This eliminates the dependency of CY and will deprecate the need of Harbor such to improve platform efficiencies by utilizing cloud native solutions and reduce resources | baseline
Resiliency | WEST Standalone Account | WEST Asset RMF (0-3) | Feb 2026 | Apr 2026 | Create WEST asset and get account IATT
Resiliency | WEST Standalone Account | WEST Standalone Asset Discovery | Apr 2026 | Oct 2026 | Discover phase of west standalone
Resiliency | WEST Standalone Account | WEST Standalone Account Build | Jun 2026 | Oct 2026 | Wrap up standalone west potential
Resiliency | EAST -> West Failover | EAST -> WEST Failover Discovery | Jun 2026 | Aug 2026
Resiliency | EAST -> West Failover | EAST -> WEST Failover Implementation | Aug 2026 | Apr 2027
Resiliency | EAST -> West Failover | EAST -> WEST Failover Testing | Mar 2027 | Jul 2027
Resiliency | FIS Implementation | FIS Support | Dec 2025 | Dec 2027
Core Support Services | AI Enablements | Platform AI assistant beta | Jul 2026 | Mar 2027 | Operator productivity tooling
Core Support Services | Landing Page | Unified platform portal | Feb 2026 | Jun 2026 | Single entry point for tenants
FVEY C2S Core | FVEY C2S Core | Cross-domain service mesh | Apr 2026 | Oct 2026 | Secure multi-domain networking
FVEY C2S Support | FVEY C2S Support | FVEY compliance automation | May 2026 | Dec 2026 | Continuous compliance enforcement
DEV C2S Core | DEV C2S Core | DEV enclave platform baseline | Dec 2025 | Jun 2026 | Initial DEV enclave rollout
DEV C2S Support | DEV C2S Support | DEV enclave operational tooling | Mar 2026 | Sep 2026 | Logging monitoring and support tooling

## Releases
release | start | end
R22 | Dec 2025 | Feb 2026
R23 | Mar 2026 | May 2026
R24 | Jun 2026 | Aug 2026
R25 | Sep 2026 | Nov 2026
R26 | Dec 2026 | Feb 2027
R27 | Mar 2027 | May 2027
R28 | Jun 2027 | Aug 2027
R29 | Sep 2027 | Dec 2027